## Defines
Modules | Team Member | Activity
MASTER | Aakash | CODING
SENSOR | Halak | DESIGN
GPS/Compass/Bridge | Vidushi | DOCUMENTATION
BRIDGE | Jay | CODE COMMENTING
BLUETOOTH | Akshata | UNIT TESTING
MOTOR | Prashant | REQUIREMENT UNDERSTANDING
HARDWARE | Saumil | REQUIREMENT ANALYSIS
| Vatsal | VERIFICATION AND VALIDATION
UI DEVELOPMENT
SUPPORT
OTHER

## Tracking Sheet
Date | Week | Activity | Team Member | Description | Hours | Module
2019-03-29 | 5 | UI DEVELOPMENT | Aakash | 1. Started designing GUI | 2 | MASTER
2019-03-29 | 5 | CODING | Aakash | 1. Interfacing Ultrasound HC-SR04 sensor with Sjone board. 2. Interfacing MaxBotix sensor with Sjone board. | 6 | SENSOR
2019-03-29 | 5 | Documentation | Vidushi | 1. Updated wiki schedule and BOM 2. Updated High Level Software Architecture and Team Member details on Wiki. | 6 | WIKI Report
2019-03-30 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of Bluetooth HC-05 Module with Sjone board and 5V power supply. 2. Worked on Data Mode(Rx/Tx) of HC-05. 3. Tested interfacing and working(Rx/TX) with Serial Monitor. | 6 | BRIDGE
2019-03-31 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of Bluetooth HC-05 Module withUBS TTL Convertor to configure Module. 2. Worked on Command Mode of HC-05 and configured with name Tech_Savy and changed config setting to 38400. 3. Refactoring of code for Bridge communication 4. Implemented C wrapper for UART2.cpp, uart_dev.cpp and for switch and LED files. 5. Testing done with Sample HC-05 BLE Android Application. | Almost Full Day | BRIDGE
2019-03-31 | 5 | Android App Development | Saumil | 1. Designed a simple app to discovery bluetooth devices nearby 2. Added buttons to turn ON and OFF bluetooth on the android phone. 3. Displayed the discovered bluetooth devices in a list view | 8 | BRIDGE
2019-04-01 | 5 | Documentation & Interfacing | Vidushi | 1. Pushed Bridge code to gitlab 2. Hardware Interfaced compass with Sjone Board (5v) | 2 | BRIDGE & GEO
2019-04-02 | 5 | Data Sheet Reviewing | Vidushi | 1. Go through CMPS 11 datasheet in i2c & Serial Mode and read about it register settings and configurations | 2 | CMPS 11 - GEO
2019-04-03 | 5 | Documentation | Vidushi | 1. Updated wiki report with Project Title details and Car Top & side views. 2. Added Abstract and How self driving car works on Wiki. 3. Added Introduction & onjectives of Tech Savy on Wiki with High Level System Design. | 3 | WIKI Report
2019-04-04 | 5 | Documentation | Vidushi | 1. Updated wiki report with Team Members & Technical Responsibilities. 2. Updated wiki report with Team Members & Administrative Responsibilities. 3. Updated wiki report with Team Deliverables Schedule. 4. Added BILL OF MATERIALS (GENERAL PARTS) and Details on the Wiki. 5. Changed the Wiki Font , format and design for our team and added color codes for all modules. | 4 | WIKI Report
2019-04-05 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Interfacing of CMPS11 with SJONE board on 3.3V. 2. Interfaced & Implement I2C Mode with CMP11 on SJOne. 3. Worked on all axis Calibration of CMPS11 using registers 0xF0, 0xF5 and 0xF6. 4. Implemented start & stop caliberation mode for CMPS 11 using command registers on SWITCH. 5. Implemented factory caliberation mode for CMPS11 on Switch in order to revert caliberation. | 4 | GEO - CMPS11
2019-04-06 | 5 | Interfacing, Coding & Testing | Vidushi | 1. Study & Implemented I2C Read/Write functions for CMPS11. 2. Implemented Heading Angle Calculation Functionality for CMPS11. 3. Refactoring of code for Geo Controller. 4. Implemented C wrapper for I2C2.cpp. | 4 | GEO - CMPS11
2019-04-08 | 5 | Documentation | Vidushi | 1. Updated wiki report with Team Deliverables Schedule Till Final Demo 2. Updated HW Block Diagrams for Bluetooth and Geo Controller | 2 | WIKI Report
2019-04-10 | 4,5,6 | Hardware Design and Motor Control | Vatsal | 1. Tested RC car DC and Servo Motor with the basic PWM API driver and performed ESC calibration before starting the motor 2. Started designing schematics and PCB layout for the RC car project 3. Designed power circuit and identified the components required(BOM) 4. Updated changes to schematic based on the previous project and team's inputs 5. Helped Jay to develop motor driver implementing CAN and DBC | 20 (Combined for week 4,5,6) | PCB and Motor Controller